## Task List
Week # | Task # | Task Description | Estimated Time (Hours) | Member Responsible
8 | 1 | Drafting a participant recruitment thread and posting it in Ed Discussion | 1.5 | Cleo
8 | 2 | Responses to the thread posted in Task #1 and communication with potential participants | 1 | Cleo | Total Hours | 100
8 | 3 | Design the back-up plan | 2 | Cleo
8 | 4 | Help participants on-board | 1 | Cleo | Cleo | 100
8 | 5 | Complete weekly status check | 0.5 | Cleo
8 | 6* | (Conduct the back-up plan if necessary) | 3 | Cleo
9 | 1 | Distribute daily learning notification to participants | 0.5 | Cleo
9 | 2 | Complete weekly status check | 0.5 | Cleo
9 | 3 | Collect Weekly Feedback | 1 | Cleo
10 | 1 | Briefly analyze the weekly feedback | 1 | Cleo
10 | 2 | Distribute daily learning notification to participants | 0.5 | Cleo
10 | 3 | Prepare the submission for Intermediate Milestone 1 | 5 | Cleo
10 | 4 | Complete weekly status check | 0.5 | Cleo
10 | 5 | Collect Weekly Feedback | 1 | Cleo
INTERMEDIATE MILESTONE 1 DUE
11 | 1 | Briefly analyze the weekly feedback | 1 | Cleo
11 | 2 | Distribute daily learning notification to participants | 0.5 | Cleo
11 | 3 | Complete weekly status check | 0.5 | Cleo
11 | 4 | Collect Weekly Feedback | 1 | Cleo
12 | 1 | Briefly analyze the weekly feedback | 1 | Cleo
12 | 2 | Complete weekly status check | 0.5 | Cleo
12 | 3 | Collect Weekly Feedback | 1 | Cleo
13 | 1 | Briefly analyze the weekly feedback | 1 | Cleo
13 | 2 | Prepare the submission for Intermediate Milestone 2 | 5 | Cleo
13 | 3 | Complete weekly status check | 0.5 | Cleo
13 | 4 | Collect Weekly Feedback | 1 | Cleo
INTERMEDIATE MILESTONE 2 DUE
14 | 1 | Briefly analyze the weekly feedback | 1 | Cleo
14 | 2 | Draft the Final Paper Outline | 1 | Cleo
14 | 3 | Complete weekly status check | 0.5 | Cleo
14 | 4 | Collect Weekly Feedback | 1 | Cleo
15 | 1 | Briefly analyze the weekly feedback | 1 | Cleo
15 | 2 | Draft the Abstract, Background and Intro for the Final Paper | 2 | Cleo
15 | 3 | Complete weekly status check | 0.5 | Cleo
15 | 4 | Collect Weekly Feedback | 1 | Cleo
15 | 5 | Briefly analyze the weekly feedback | 1 | Cleo
15 | 6 | Collect final learning outcomes from participants | 2 | Cleo
16 | 1 | Input and clean the data | 3 | Cleo
16 | 2 | Synthesize Weekly Feedback from previous 6 weeks - qualitative | 5 | Cleo
16 | 3 | Student engagement analysis - quantitative | 6 | Cleo
16 | 4 | Learning outcome analysis - quantitative | 6 | Cleo
16 | 5 | Draw graphs from the data | 3 | Cleo
16 | 6 | Summarize the findings - qualitative | 5 | Cleo
16 | 7 | Complie the slides for presentation | 3 | Cleo
16 | 8 | Prepare for presentation | 5 | Cleo
16 | 9 | Compile the written paper | 16 | Cleo
16 | 10 | Profread and Polish the written paper | 2 | Cleo
16 | 11 | Assemble the final project | 3 | Cleo
FINAL PROJECT DUE
Note on A1: The week of the semester, from week 8 to week 16.
Note on B1: An identifer for each task. This is just used for easier conversation, e.g. "It looks like you didn't finish Task 5."
Note on C1: A brief (~1 sentence or fragment) description of the task.
Note on D1: The estimated number of hours to complete the task.
Note on E1: For team projects, which team member is responsible for the task.